## 📋 Cover
NimbusHR Inc. — Cybersecurity Risk Register
Aligned to NIST Cybersecurity Framework 2.0 ¦ Prepared by: Donnie V Haynes
DOCUMENT INFORMATION
Document Title | NimbusHR Cybersecurity Risk Register
Version | 1.0 — Initial Release
Prepared By | Donnie V Haynes (Portfolio Project)
Framework | NIST Cybersecurity Framework 2.0
Classification | Confidential — Internal Use Only
Review Cycle | Monthly review ¦ Annual reassessment
Last Updated | 2024
HOW TO USE THIS REGISTER
📊 Risk Register tab | The main working document. Each row is one risk. Update Status, Residual Score, and Notes as controls are implemented.
📈 Dashboard tab | Auto-calculated summary. Shows risk counts by rating, treatment strategy breakdown, and open vs closed items.
📚 Reference tab | Definitions for all column values — risk ratings, treatment strategies, status codes, and NIST CSF function descriptions.
🔄 Update frequency | The register should be reviewed monthly by the Risk Owner and formally reassessed annually or after any material security incident.
➕ Adding new risks | Insert a new row in the Risk Register, assign the next sequential Risk ID (R-009, R-010, etc.), and complete all columns.
✅ Closing a risk | When a risk is fully remediated, change Status to CLOSED and set the Residual Score to reflect remaining exposure. Do not delete rows.
RISK RATING SCALE
🔴 CRITICAL (20–25) | Immediate action required. Escalate to senior leadership.
🟠 HIGH (12–19) | Remediate within 30–60 days. Assign owner, track to closure.
🟡 MEDIUM (6–11) | Remediate within 90 days. Document compensating controls.
🟢 LOW (1–5) | Monitor and review at next scheduled assessment cycle.

## 📊 Risk Register
NimbusHR Inc. ¦ Cybersecurity Risk Register ¦ NIST CSF 2.0 ¦ Prepared by: Donnie V Haynes ¦ Version 1.0 ¦ 2024
Risk ID | Risk Title | Category | Description | Threat Source | Affected Assets | NIST CSF Ref | Likelihood (1–5) | Impact (1–5) | Inherent Risk Score | Inherent Rating | Treatment Strategy | Controls In Place | Additional Controls Required | Risk Owner | Target Date | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Rating | Status | Last Reviewed | Notes
R-001 | No MFA on Administrative Accounts | Access Control | Admin and privileged AWS accounts lack MFA. A credential compromise would grant full cloud environment access including all stored PII. | External Attacker / Insider | AWS Root Account, IAM Admin Roles, Console Access | PR.AA-03, PR.AA-05 | 5 | 5 | 25 | CRITICAL | Mitigate | Password policy enforced. IAM users require unique credentials. | Enable MFA on root account and all IAM console users. Enforce via SCP. Deploy hardware tokens for privileged accounts. | IT Manager | 2024-01-15 | 2 | 5 | 10 | MEDIUM | IN PROGRESS | 2024-01-01 | MFA enabled on root account. Rollout to IAM users underway. SCP policy drafted.
R-002 | Insufficient Encryption of PII at Rest | Data Protection | Not all S3 buckets have default encryption enabled. KMS key rotation not configured on RDS. PII exposed if buckets are misconfigured or accessed without authorisation. | External Attacker / Misconfiguration | AWS S3 Buckets, RDS Database | PR.DS-01, PR.DS-02 | 4 | 5 | 20 | CRITICAL | Mitigate | RDS encryption enabled at rest. TLS enforced in transit. | Enable S3 default encryption (AES-256/KMS) on all buckets. Enable KMS key auto-rotation. Deploy AWS Config rule for unencrypted resources. | IT Manager | 2024-01-15 | 2 | 5 | 10 | MEDIUM | IN PROGRESS | 2024-01-01 | S3 encryption audit in progress. 14 of 22 buckets remediated.
R-003 | No Incident Response Plan | Incident Readiness | No documented IRP exists. Staff have no established procedures for detection, containment, notification, or recovery in the event of a breach or ransomware incident. | All Threat Actors | All Systems / Business Continuity | RS.MA-01, RS.CO-02, RC.RP-01 | 4 | 4 | 16 | HIGH | Mitigate | None. No documented IRP, playbooks, or escalation contacts exist. | Draft IRP covering: incident classification, roles, containment, comms, and recovery. Conduct tabletop exercise within 30 days of publication. | IT Manager | 2024-02-28 | 3 | 4 | 12 | HIGH | OPEN | 2024-01-01 | IRP drafting not yet started. Assigned to IT Manager. High priority.
R-004 | No Security Awareness Training | Human Factor | No mandatory security awareness training programme. Employees are susceptible to phishing, social engineering, and unsafe data-handling practices. | Phishing / Social Engineering | All Employees / Email / Credentials | GV.RR-02, PR.AT-01 | 4 | 4 | 16 | HIGH | Mitigate | Informal guidance shared via Slack. No structured programme. | Deploy training platform (KnowBe4 free tier or equivalent). Require annual completion. Run quarterly simulated phishing campaigns. | HR + IT Manager | 2024-02-28 | 2 | 4 | 8 | MEDIUM | OPEN | 2024-01-01 | Evaluating KnowBe4 and Proofpoint free tiers. Budget approval pending.
R-005 | No Patch Management Programme | Patch Management | No documented patching schedule. Open-source library dependencies in the web application may contain known CVEs. No vulnerability scanner deployed. | External Attacker / Opportunistic | Web Application, AWS EC2, OS / Libraries | ID.RA-01, PR.PS-02 | 3 | 4 | 12 | HIGH | Mitigate | Ad-hoc patching performed by developers. No formal SLA. | Define monthly patch cycle. Deploy Dependabot in GitHub CI/CD. Deploy AWS Inspector for infrastructure scanning. Set CVE SLAs. | Engineering Lead | 2024-03-31 | 2 | 4 | 8 | MEDIUM | OPEN | 2024-01-01 | Dependabot can be enabled on GitHub at no cost. Quick win.
R-006 | Excessive Privileges / No Access Reviews | Access Control | Developer and support accounts hold broader IAM permissions than role requires. No formal access review. Former employees may retain active credentials. | Insider Threat / Compromised Account | AWS IAM, Internal Systems, S3, RDS | PR.AA-01, PR.AA-05, ID.AM-03 | 3 | 3 | 9 | MEDIUM | Mitigate | Unique IAM credentials per user. No shared accounts. | Conduct immediate IAM access review. Implement least-privilege. Create off-boarding checklist. Schedule quarterly access certifications. | IT Manager | 2024-03-31 | 2 | 3 | 6 | MEDIUM | OPEN | 2024-01-01 | IAM Access Analyzer available at no cost in AWS console.
R-007 | Insufficient Logging and Monitoring | Incident Readiness | CloudTrail enabled but logs not actively monitored. No alerts on critical events. Attackers could operate undetected for extended periods. | All Threat Actors | AWS CloudTrail, CloudWatch, All Infrastructure | DE.CM-01, DE.AE-02, PR.PS-04 | 3 | 3 | 9 | MEDIUM | Mitigate | AWS CloudTrail enabled in primary region. Logs stored in S3. | Enable CloudTrail in all regions. Configure CloudWatch alerts for: root logins, IAM changes, large S3 downloads, failed auth spikes. | IT Manager | 2024-03-31 | 2 | 3 | 6 | MEDIUM | OPEN | 2024-01-01 | CloudWatch alerting is low-cost. Estimate <$20/month for alert rules.
R-008 | Unassessed Third-Party Vendor Risk | Third-Party Risk | Payroll API integration transmits salary and banking data to a third party that has not been formally security assessed. No DPA or VSQ in place. | Supply Chain / Third-Party Breach | Payroll Integration API, Client Salary Data | GV.SC-04, GV.SC-06 | 2 | 3 | 6 | MEDIUM | Transfer | TLS encryption on API calls. Contractual SLA with vendor. | Issue vendor security questionnaire (VSQ). Request SOC 2 report. Ensure Data Processing Agreement (DPA) is executed. | Legal + IT Manager | 2024-04-30 | 2 | 3 | 6 | MEDIUM | OPEN | 2024-01-01 | VSQ template available from NIST SP 800-161. Low effort, high value.

## 📈 Dashboard
NimbusHR Risk Register — Executive Dashboard
Auto-calculated from Risk Register ¦ Prepared by: Donnie V Haynes ¦ NIST CSF 2.0
▸ RISK COUNTS — INHERENT RATING
🔴 CRITICAL risks | 2
🟠 HIGH risks | 3
🟡 MEDIUM risks | 3
🟢 LOW risks | 0
📋 Total risks | 8
▸ RISK STATUS BREAKDOWN
🔓 Open | 6
🔄 In Progress | 2
✅ Closed | 0
📌 Accepted | 0
▸ TREATMENT STRATEGY BREAKDOWN
🛡️ Mitigate | 7
🔄 Transfer | 1
📋 Accept | 0
🚫 Avoid | 0
▸ RISK REDUCTION SUMMARY (Inherent vs Residual)
Risk ID | Risk Title | Inherent Score | Residual Score | Score Reduction
R-001 | No MFA on Administrative Accounts | 25 | 10 | 15
R-002 | Insufficient Encryption of PII at Rest | 20 | 10 | 10
R-003 | No Incident Response Plan | 16 | 12 | 4
R-004 | No Security Awareness Training | 16 | 8 | 8
R-005 | No Patch Management Programme | 12 | 8 | 4
R-006 | Excessive Privileges / No Access Reviews | 9 | 6 | 3
R-007 | Insufficient Logging and Monitoring | 9 | 6 | 3
R-008 | Unassessed Third-Party Vendor Risk | 6 | 6 | 0

## 📚 Reference
Reference Guide — Definitions & Framework Mappings
RISK RATING SCALE
CRITICAL (Score 20–25) | Immediate remediation required. Escalate to senior leadership. Risk to core business operations.
HIGH (Score 12–19) | Remediate within 30–60 days. Assign a named owner. Track to closure at every review.
MEDIUM (Score 6–11) | Remediate within 90 days. Document any compensating controls in place.
LOW (Score 1–5) | Monitor at next scheduled review cycle. Compensating controls may be sufficient.
TREATMENT STRATEGIES
Mitigate | Implement controls to reduce likelihood or impact. Most common strategy — applies to the majority of technical risks.
Transfer | Shift financial liability to a third party (e.g., cyber liability insurance, contractual indemnity, managed security provider).
Accept | Acknowledge the risk exists but make a documented decision that cost of remediation exceeds benefit. Requires management sign-off.
Avoid | Eliminate the activity or system that creates the risk entirely. E.g., stop using an insecure third-party tool.
STATUS CODES
OPEN | Risk identified. No remediation action taken yet. Requires an assigned owner and target date.
IN PROGRESS | Remediation underway. Controls being implemented. Check notes column for progress details.
CLOSED | Risk fully remediated. Controls implemented and verified. Residual score updated to reflect remaining exposure.
ACCEPTED | Risk formally accepted by management. Documented rationale required. Review at next cycle.
NIST CSF 2.0 — CORE FUNCTIONS
GOVERN (GV) | Establishes organizational context, risk strategy, roles, policies, and oversight. New in CSF 2.0. Foundation of all other functions.
IDENTIFY (ID) | Understand the organization's assets, risks, and vulnerabilities. Includes asset management and risk assessment.
PROTECT (PR) | Implement safeguards to limit the impact of cybersecurity events. Includes access control, data protection, and training.
DETECT (DE) | Develop and implement activities to identify cybersecurity events in a timely manner. Includes monitoring and anomaly detection.
RESPOND (RS) | Take action regarding a detected cybersecurity incident. Includes response planning, communications, and analysis.
RECOVER (RC) | Restore capabilities impaired by a cybersecurity incident. Includes recovery planning and communications.
RISK SCORING METHODOLOGY
Inherent Risk Score | Likelihood (1–5) × Impact (1–5) = Raw score BEFORE any controls are applied. Represents worst-case exposure.
Residual Risk Score | Likelihood (1–5) × Impact (1–5) = Score AFTER controls are implemented. Should decrease as remediation progresses.
Likelihood Scale | 1=Rare, 2=Unlikely, 3=Possible, 4=Likely, 5=Almost Certain. Based on threat frequency and existing control environment.
Impact Scale | 1=Negligible, 2=Minor, 3=Moderate, 4=Major, 5=Catastrophic. Based on financial, reputational, legal, and operational impact.